## Timeline & Milestones
ENTERPRISE PLATFORM MIGRATION — TIMELINE & MILESTONE TRACKER
Update % Complete and Actual Start/End dates as work progresses. Status auto-updates. Compatible with import to Jira (CSV) and Smartsheet.
SUMMARY DASHBOARD |  |  | 27 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0%
# | Phase | Task / Milestone | Owner | Priority | Planned Start | Planned End | Actual Start | Actual End | Duration (Days) | % Complete | Status | Dependencies | Notes / Blockers | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18 | Wk 19 | Wk 20
[14 empty] | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20
1 | Discovery | Define migration scope and objectives | Prog. Manager | High | Week 1 | Week 2 |  |  | 10 | 0% | Not Started |  | Kick-off meeting completed | bar: Wk 1 W1 to Wk 2 W2
2 | Discovery | Inventory current-state systems | Technical Lead | Critical | Week 1 | Week 3 |  |  | 14 | 0% | Not Started | Task 1 | Dependency scanner tool | bar: Wk 1 W1 to Wk 3 W3
3 | Discovery | Stakeholder interviews & requirements | Prog. Manager | High | Week 2 | Week 4 |  |  | 10 | 0% | Not Started | Task 1 | Schedule within first 2 weeks | bar: Wk 2 W2 to Wk 4 W4
4 | Discovery | Risk assessment and scoring | Prog. Manager + Tech Lead | High | Week 2 | Week 4 |  |  | 7 | 0% | Not Started | Task 2 | Complete Risk Matrix sheet | bar: Wk 2 W2 to Wk 4 W4
5 | Discovery | Executive sponsor scope sign-off | Program Manager | Critical | Week 4 | Week 4 |  |  | 2 | 0% | Not Started | Tasks 1–4 | Gate 1 — must complete before planning | bar: Wk 4 W4
6 | Planning | Develop migration runbooks (all waves) | Technical Lead | Critical | Week 5 | Week 8 |  |  | 21 | 0% | Not Started | Task 5 | One runbook per wave | bar: Wk 5 W5 to Wk 8 W8
7 | Planning | Define go/no-go criteria | Tech Lead + Eng. Mgr | Critical | Week 5 | Week 6 |  |  | 7 | 0% | Not Started | Task 5 | Document in runbook header | bar: Wk 5 W5 to Wk 6 W6
8 | Planning | Create stakeholder communication plan | Comms Lead | High | Week 5 | Week 7 |  |  | 10 | 0% | Not Started | Task 3 | Use Comms Plan sheet | bar: Wk 5 W5 to Wk 7 W7
9 | Planning | Schedule migration windows | Technical Lead | High | Week 6 | Week 7 |  |  | 5 | 0% | Not Started | Task 6 | Coordinate with infra and ops | bar: Wk 6 W6 to Wk 7 W7
10 | Planning | Legal / compliance review gate | Legal / CISO | Critical | Week 7 | Week 8 |  |  | 5 | 0% | Not Started | Tasks 6–9 | Gate 2 — blocker for pilot | bar: Wk 7 W7 to Wk 8 W8
11 | Pilot | Configure pilot environment (Wave 0) | Cloud Eng. | Critical | Week 9 | Week 10 |  |  | 7 | 0% | Not Started | Task 10 | Mirrors production subset | bar: Wk 9 W9 to Wk 10 W10
12 | Pilot | Execute Wave 0 pilot migration | Technical Lead | Critical | Week 10 | Week 11 |  |  | 3 | 0% | Not Started | Task 11 | Limited blast radius | bar: Wk 10 W10 to Wk 11 W11
13 | Pilot | Data integrity validation post-pilot | Data Engineer | Critical | Week 11 | Week 11 |  |  | 2 | 0% | Not Started | Task 12 | Checksum + row count reconciliation | bar: Wk 11 W11
14 | Pilot | User acceptance testing (UAT) | QA Lead | High | Week 11 | Week 12 |  |  | 5 | 0% | Not Started | Task 12 | Business sign-off required | bar: Wk 11 W11 to Wk 12 W12
15 | Pilot | Update runbooks with pilot learnings | Technical Lead | High | Week 12 | Week 12 |  |  | 3 | 0% | Not Started | Tasks 12–14 | Gate 3 — approval to proceed | bar: Wk 12 W12
16 | Pilot | Gate review: approve production waves | Exec. Sponsor | Critical | Week 12 | Week 12 |  |  | 1 | 0% | Not Started | Task 15 | Decision: proceed / defer / cancel | bar: Wk 12 W12
17 | Execution | Send T–72h stakeholder notifications | Comms Lead | High | Week 13 | Week 13 |  |  | 1 | 0% | Not Started | Task 16 | Per communication plan | bar: Wk 13 W13
18 | Execution | Execute Wave 1 production migration | Technical Lead | Critical | Week 13 | Week 13 |  |  | 2 | 0% | Not Started | Task 17 | Overnight window preferred | bar: Wk 13 W13
19 | Execution | Wave 1 validation and sign-off | Tech Lead + Data Eng. | Critical | Week 13 | Week 14 |  |  | 1 | 0% | Not Started | Task 18 | Within 4 hrs of cutover close | bar: Wk 13 W13 to Wk 14 W14
20 | Execution | Execute Wave 2 production migration | Technical Lead | Critical | Week 14 | Week 14 |  |  | 2 | 0% | Not Started | Task 19 | 1-week gap from Wave 1 | bar: Wk 14 W14
21 | Execution | Execute Wave 3 (final) migration | Technical Lead | Critical | Week 15 | Week 15 |  |  | 2 | 0% | Not Started | Task 20 | Final wave | bar: Wk 15 W15
22 | Execution | Wave 3 validation and business sign-off | Tech Lead + Business | Critical | Week 15 | Week 16 |  |  | 2 | 0% | Not Started | Task 21 | All systems green | bar: Wk 15 W15 to Wk 16 W16
23 | Stabilization | Hypercare monitoring (Week 1) | Technical Lead | High | Week 16 | Week 17 |  |  | 7 | 0% | Not Started | Task 22 | Daily standups; war room on standby | bar: Wk 16 W16 to Wk 17 W17
24 | Stabilization | Hypercare monitoring (Week 2) | Technical Lead | High | Week 17 | Week 18 |  |  | 7 | 0% | Not Started | Task 23 | Reduce to on-call only if stable | bar: Wk 17 W17 to Wk 18 W18
25 | Stabilization | Decommission legacy environment | Cloud Eng. | High | Week 18 | Week 19 |  |  | 5 | 0% | Not Started | Task 24 | Requires exec sign-off | bar: Wk 18 W18 to Wk 19 W19
26 | Stabilization | Project retrospective | Program Manager | Medium | Week 19 | Week 19 |  |  | 2 | 0% | Not Started | Task 25 | Capture lessons learned | bar: Wk 19 W19
27 | Stabilization | Executive close-out report | Program Manager | High | Week 19 | Week 20 |  |  | 3 | 0% | Not Started | Task 26 | Final deliverable | bar: Wk 19 W19 to Wk 20 W20