## RACI Template
ENTERPRISE PLATFORM MIGRATION — RACI RESPONSIBILITY MATRIX
LEGEND: | R | Responsible — Does the work | A | Accountable — Final decision / sign-off | C | Consulted — Provides input; two-way | I | Informed — Kept up to date; one-way
|  |  | Executive Sponsor | Program Manager | Technical Lead | Engineering Manager | Security Engineer | Data Engineer | Cloud/Infra Engineer | QA / Testing | Change Mgmt / Comms | Legal / Compliance | Vendor / Partner | Business Stakeholder | End User Rep
# | Phase | Activity / Decision
1.1 | Discovery | Define migration scope and objectives | A | R | C | C | C | C | C |  | C | C | I | C | I
1.2 | Discovery | Inventory current-state systems and dependencies | I | C | R | A | C | C | R | C |  | I | C |  | I
1.3 | Discovery | Conduct stakeholder interviews and requirements gathering | I | R | C | C |  | C |  |  | A | C |  | R | R
1.4 | Discovery | Complete risk assessment and scoring | C | A | R | C | R | C | C | C | C | C | C | I
1.5 | Discovery | Obtain executive sponsor sign-off on scope | C: A; A: R; R: C; C: C; C: C; I: I
2.1 | Planning | Develop detailed migration runbooks per wave | I | C | A/R | R | R | R | R | C |  | C | C |  | I
2.2 | Planning | Define go/no-go criteria and rollback thresholds | C | A | R | R | R | C | R | R |  | C | C | C
2.3 | Planning | Create stakeholder communication plan | [8 empty] | R | C | I | C | C | bar: A I to C R
2.4 | Planning | Establish RACI and escalation matrix | C | A/R | C | C | C | C | C | C | C | C | C | C
2.5 | Planning | Schedule migration windows and freeze periods | I | A | R | R | C | C | R | C | C |  | C | C
2.6 | Planning | Complete compliance and legal review gate | [9 empty] | A | C |  | I | bar: I to C; R to C
3.1 | Pilot | Execute pilot migration (Wave 0) | I | A | R | R | R | R | R | R |  | C | C |  | I
3.2 | Pilot | Validate data integrity post-pilot | I | C | C | R | C | A | R | R |  | C | C |  | I
3.3 | Pilot | Conduct user acceptance testing (UAT) | I | C | C | R | C | C | C | A |  |  |  | R | R
3.4 | Pilot | Document lessons learned; update runbooks | I | R | A | R | C | C | C | C | C |  | C | C
3.5 | Pilot | Gate review: approve or defer production waves | A | R | C | C | C | C | C | C | C | C | C | C
4.1 | Execution | Send pre-migration stakeholder notification | I I I: I; C C R: C; R A C: A/R | I | I | I | I
4.2 | Execution | Execute production migration waves | I | A | R | R | R | R | R | R |  |  | C | I | I
4.3 | Execution | Monitor system health during cutover | I | C | R | R | A | C | R | R |  |  | C | I
4.4 | Execution | Authorize go/no-go at each wave gate | A | R | C | C | C | C | C | C |  | C |  | C
4.5 | Execution | Execute rollback (if triggered) | I | A | R | R | R | C | R | C | C | C | R | I
5.1 | Stabilization | Hypercare monitoring (2-week window) | I | A | R | R | R | C | R | R | C |  | C | I | I
5.2 | Stabilization | Decommission legacy environment | C | A | R | R | R | C | R | C |  | C | C
5.3 | Stabilization | Conduct retrospective and lessons learned | C | A/R | R | R | R | R | R | R | R | C | C | C | C
5.4 | Stabilization | Close project; archive documentation | I | A/R | C | C |  | C | C |  | C | C |  | I