## Risk Assessment Matrix
ENTERPRISE PLATFORM MIGRATION — RISK ASSESSMENT MATRIX
Score each risk: Probability (1–5) × Impact (1–5) = Risk Score ¦ 25 = Critical ¦ 15–24 = High ¦ 8–14 = Medium ¦ 1–7 = Low
SCORING GUIDE |  |  | PROBABILITY × IMPACT HEAT MAP
1 | Rare / Negligible | Rare / Negligible | Impact → | 1-Negligible | 2-Minor | 3-Moderate | 4-Major | 5-Critical
2 | Unlikely / Minor |  | 5 Certain | 5 | 10 | 15 | 20 | 25
3 | Possible / Moderate |  | 4 Likely | 4 | 8 | 12 | 16 | 20
4 | Likely / Major |  | 3 Possible | 3 | 6 | 9 | 12 | 15
5 | Almost Certain / Critical |  | 2 Unlikely | 2 | 4 | 6 | 8 | 10
|  |  | 1 Rare | 1 | 2 | 3 | 4 | 5
# | Risk ID | Risk Description | Category | Probability (1–5) | Impact (1–5) | Risk Score | Rating | Owner | Mitigation Strategy | Contingency Plan | Status
1 | RISK-001 | Incomplete dependency mapping leads to broken integrations post-cutover | Technical | 4 | 5 | 20 | CRITICAL | TBD — Assign Owner | Assign dedicated discovery sprint; use automated dependency scanner | Rollback to source environment; incident bridge call within 15 min | Open
2 | RISK-002 | Data integrity loss during migration of 20M+ records | Data | 3 | 5 | 15 | HIGH | TBD — Assign Owner | Pre/post row-count reconciliation; checksum validation at each wave | Restore from pre-migration snapshot; data quality review board | Open
3 | RISK-003 | Key SME unavailable during critical migration window | Resource | 3 | 4 | 12 | HIGH | TBD — Assign Owner | Document all SME knowledge; cross-train backup; lock SME calendars | Escalate to executive sponsor; defer wave if no qualified backup | Open
4 | RISK-004 | Network latency spikes cause timeout failures during data movement | Infrastructure | 3 | 3 | 9 | MEDIUM | TBD — Assign Owner | Schedule migrations during low-traffic windows; throttle transfer rate | Pause migration; reroute via secondary path; resume next window | Open
5 | RISK-005 | Secrets/credentials not rotated prior to cutover causing auth failures | Security | 2 | 5 | 10 | MEDIUM | TBD — Assign Owner | Secrets rotation checklist in pre-migration runbook; vault audit | Emergency credential rotation; engage security team on-call | Open
6 | RISK-006 | Stakeholder misalignment on go/no-go criteria delays migration | Governance | 3 | 3 | 9 | MEDIUM | TBD — Assign Owner | Pre-align criteria in RACI; gate review 72h before each wave | Escalation path defined; sponsor has final authority on timeline | Open
7 | RISK-007 | Monitoring gaps during transition leave incidents undetected | Observability | 4 | 4 | 16 | HIGH | TBD — Assign Owner | Run dual monitoring (old + new) for 2-week overlap period | Revert to legacy monitoring; manual watchlist for critical services | Open
8 | RISK-008 | Rollback procedure untested; team unable to execute under pressure | Process | 2 | 5 | 10 | MEDIUM | TBD — Assign Owner | Mandatory rollback dry-run in staging; document step-by-step with timing | Engage vendor support; war room with 30-min decision checkpoint | Open
9 | RISK-009 | Compliance/regulatory requirements missed during planning | Compliance | 2 | 4 | 8 | MEDIUM | TBD — Assign Owner | Legal/compliance review gate before Phase 2; HIPAA/PCI checklist | Halt migration; legal review; remediate before resuming | Open
10 | RISK-010 | End-user change fatigue causes resistance and low adoption | Change Mgmt | 3 | 2 | 6 | MEDIUM | TBD — Assign Owner | Communication plan; training sessions 2 weeks before cutover | Hypercare support team; feedback loop to PM for rapid resolution | Open