## Stakeholder Comms Plan
ENTERPRISE PLATFORM MIGRATION — STAKEHOLDER COMMUNICATION PLAN
Purpose: Ensure all stakeholders receive the right information, at the right time, through the right channel — throughout the migration lifecycle.
SECTION A — STAKEHOLDER REGISTER
Stakeholder Group | Role / Title | Interest Level (H/M/L) | Influence Level (H/M/L) | Engagement Strategy | Primary Contact | Backup Contact | Preferred Channel | Concerns / Notes | Last Updated
Executive Sponsor | VP Engineering / CTO | H | H | Keep satisfied; brief weekly; get sign-offs | TBD | TBD | Email + Exec Briefing | Concerned with business continuity and budget | —
Engineering Managers | Director / Sr. Eng. Mgr | H | H | Collaborate; include in gate reviews; daily standups | TBD | TBD | Slack + Jira | Need clear runbooks and escalation paths | —
Product Management | Director of Product | H | M | Inform of feature freeze windows; get buy-in on timeline | TBD | TBD | Email + Weekly Sync | Impact on roadmap during migration freeze | —
Security & Compliance | CISO / Security Eng. | M | H | Consult on secrets mgmt and compliance gates | TBD | TBD | Email + Security Review | PCI/HIPAA compliance continuity | —
Data Engineering | Data Eng. Lead | H | M | Involve in data validation; review checksum reports | TBD | TBD | Slack + Data Review | Data integrity and pipeline continuity | —
End Users / Business | Business Unit Leads | M | M | Communicate downtime windows; provide FAQs and training | TBD | TBD | Email + Town Hall | Downtime impact; workflow disruption | —
Customer Success | CS Managers | M | L | Brief on any customer-facing impact; provide talking points | TBD | TBD | Email + Slack | Customer SLA implications | —
Legal / Risk | General Counsel / Risk | L | H | Notify of compliance gates; obtain sign-off | TBD | TBD | Email | Regulatory and contractual risk | —
Vendor / Partner | Platform Vendor CSM | M | M | Include in technical planning; manage SLAs | TBD | TBD | Email + Meetings | Support availability during migration windows | —
Change Management | Change Mgmt Lead | H | M | Co-create comms; lead training and readiness | TBD | TBD | All channels | Adoption and resistance management | —
SECTION B — COMMUNICATION EVENTS SCHEDULE
Communication Event | Trigger / Timing | Audience | Owner | Channel | Format | Key Message | Success Metric | Phase | Status
Migration Kick-off Announcement | Project start — Week 1 | All stakeholders | Program Manager | Email + All-Hands | Slide deck + FAQ | Scope, timeline, impact, and support resources | 90%+ open rate; <5 escalations | Discovery | Planned
Weekly Status Report | Every Friday — Ongoing | Executive Sponsor, Eng. Managers | Program Manager | Email | Dashboard + 1-pager | RAG status, risks, decisions needed, next week plan | Distributed within 2 hrs of EOD Friday | All | Planned
Pre-Wave Notification (T–72h) | 72 hours before each wave | All stakeholders | Comms Lead | Email + Slack | Template email | Window timing, expected impact, rollback trigger criteria | No surprises at cutover; stakeholders confirm receipt | Execution | Planned
Pre-Wave Notification (T–24h) | 24 hours before each wave | Impacted end users | Comms Lead | Email | Short-form alert | Final reminder: what changes, when, who to contact | User helpdesk call volume within expected range | Execution | Planned
Go/No-Go Decision Brief | 2 hrs before each production wave | Exec Sponsor, Eng. Leads | Program Manager | Bridge call | Decision brief | Readiness scorecard; risks; go/no-go recommendation | Decision made and documented before window opens | Execution | Planned
Cutover Status Updates | Every 30 min during migration window | Engineering leads | Technical Lead | Slack war-room channel | Real-time updates | Health check results; progress vs. plan; blockers | No silent gaps >30 min during active window | Execution | Planned
Migration Complete Notification | Within 1 hr of successful cutover | All stakeholders | Comms Lead | Email + Slack | Brief update | Confirmation, validation results, hypercare contacts | Sent within 60 min of cutover close | Execution | Planned
Rollback Notification (if triggered) | Immediately upon rollback decision | All stakeholders | Program Manager | Email + Phone | Urgent alert | What happened, what's being done, next steps, ETA | Sent within 15 min of decision; exec brief within 30 min | Execution | Conditional
Hypercare Check-in | Daily — first 2 weeks post-cutover | Eng. Managers, Business leads | Technical Lead | Standup + Slack | 15-min standup | Open incidents, performance metrics, user issues | All P1/P2 issues resolved within SLA | Stabilization | Planned
Post-Migration Retrospective | 2 weeks after final wave | Full project team | Program Manager | Workshop | Facilitated retro | What went well, what didn't, action items for next migration | Action items documented and assigned within 48 hrs | Stabilization | Planned
Executive Close-out Report | Project close | Executive Sponsor, Leadership | Program Manager | Email + Presentation | Executive report | Outcomes vs. plan, lessons learned, cost/time actuals | Delivered within 5 business days of project close | Stabilization | Planned